## Summary
Metric | Count
Sitemap rows | 45
Added | 8
Modified | 4
Redirects | 2
Decisions pending | 1
Navigation rows | 40
Nav rows added | 6
Checklist tasks | 43
Done | 0
Blocked | 0
Open decisions | 13
Unanswered | 13
How to use
Sitemap and Navigation: final proposed structure; review Change and Reason columns.
Redirects & Canonicals: hand to SEO/Developer.
Build Checklist: update Status (dropdown); Summary counts update automatically.
Open Decisions: fill the Answer column; items block the gates shown.

## Sitemap
Path | Nav group | Page type | Owner | Page job | Launch priority | Template | Notes | Change | Reason for change
/ | Home | Homepage | Shopify UX Designer | Route users by intent: gift, corporate, vegan, shop | Must launch | Homepage | Hero, intent cards, bestsellers, corporate, vegan, delivery trust | Unchanged
/collections/all | Shop | Collection | Ecommerce Trader | Full catalogue browsing | Must launch | Collection PLP | Use broad filters only here | Unchanged
/collections/pralines-and-truffles | Shop | Collection | Ecommerce Trader | Core category revenue and Belgian product truth | Must launch | Collection PLP | Filters: price, box size, chocolate type, filling, alcohol | Unchanged
/collections/ballotins | Shop | Collection | Ecommerce Trader | Heritage product format | Must launch | Collection PLP | 250g, 500g, 1kg variants | Unchanged
/collections/gift-boxes | Shop/Gifts | Collection | Ecommerce Trader | Core gift conversion | Must launch | Collection PLP | Show occasion chips | Unchanged
/collections/chocolate-tablets | Shop | Collection | Ecommerce Trader | Lower-price entry and add-on product | Phase 1 | Collection PLP | Useful for vegan and dark chocolate | Unchanged
/collections/small-gifts | Shop/Gifts | Collection | Ecommerce Trader | Low-friction gifting under entry price | Must launch | Collection PLP | Pair with gift message | Modified | Absorbs /collections/small-attentions (redirect). Design uses "Small Attentions" as the customer-facing label.
/collections/premium-gifts | Shop/Gifts | Collection | Ecommerce Trader | AOV driver | Must launch | Collection PLP | Premium image style | Unchanged
/collections/belgian-classics | Shop | Collection | Ecommerce Trader | Heritage and SEO route | Phase 1 | Collection PLP | Pralines, ballotins, truffles | Unchanged
/collections/seasonal-drops | Shop/Gifts | Collection | Ecommerce Trader | Campaign and urgency driver | Phase 1 | Collection PLP | Can be manually curated | Unchanged
/collections/birthday-gifts | Gifts | Collection | Ecommerce Trader | Occasion landing page | Phase 1 | Gift PLP | SEO and paid search landing | Unchanged
/collections/thank-you-gifts | Gifts | Collection | Ecommerce Trader | Occasion landing page | Must launch | Gift PLP | Strong corporate crossover | Unchanged
/collections/love-and-romance | Gifts | Collection | Ecommerce Trader | Occasion landing page | Phase 1 | Gift PLP | Valentine later | Unchanged
/collections/dinner-party-gifts | Gifts | Collection | Ecommerce Trader | Host gift route | Phase 1 | Gift PLP | Good for small gifts | Unchanged
/collections/vegan-chocolates | Vegan & Conscious | Collection | Ecommerce Trader | Growth and values-led buyer route | Must launch | Vegan PLP | Self-canonical SEO collection | Modified | Mockup shows Organic/Fair Trade tiles and "No palm oil" claim: only show if SKU-level proof exists (see Open Decisions).
/collections/organic-chocolate | Vegan & Conscious | Collection | Ecommerce Trader/SEO | Claim landing page if true at SKU level | Phase 1 if claims exist | Collection PLP | Do not create if not supported by products | Unchanged
/collections/fairtrade-chocolate | Vegan & Conscious | Collection | Ecommerce Trader/SEO | Claim landing page if true at SKU level | Phase 1 if claims exist | Collection PLP | Do not create if not supported by products | Unchanged
/collections/no-alcohol-chocolates | Vegan & Conscious | Collection | Ecommerce Trader | Dietary/trust gift route | Must launch if data supports | Collection PLP | Useful for gifting | Unchanged
/collections/corporate-gifts | Corporate Gifts | Collection | Ecommerce Trader | Business gift product collection | Must launch | Corporate PLP | Not normal retail clutter | Unchanged
/pages/corporate-gifting | Corporate Gifts | Landing page | Shopify UX Designer | B2B funnel and value proposition | Must launch | Corporate Landing | Use cases, product formats, personalisation, quote | Modified | Mockup adds Seasonal and Hospitality use cases, multi-address, invoicing: confirm scope before build.
/pages/pralines-with-logo | Corporate Gifts | Landing page | Shopify UX Designer | Logo pralines conversion page | Must launch | Corporate Landing | Inspired by Van Parijs | Unchanged
/pages/client-gifts | Corporate Gifts | Landing page | Ecommerce Trader | Specific B2B use case | Phase 1 | Corporate Landing | Can be copy-light at launch | Unchanged
/pages/employee-gifts | Corporate Gifts | Landing page | Ecommerce Trader | Specific B2B use case | Phase 1 | Corporate Landing | Useful for HR/bulk | Unchanged
/pages/request-a-quote | Corporate Gifts | Form page | Shopify Developer | B2B quote capture | Must launch | Quote Form | Quantity, budget, date, upload logo | Unchanged
/pages/upload-your-logo | Corporate Gifts | Form page | Shopify Developer | Logo upload and artwork intake | Must launch | Upload Form | File type guidance | Unchanged
/pages/belgian-pralines | Our Chocolate | Trust/SEO page | Brand Designer/SEO | Heritage and product education | Must launch | Editorial Trust | Supports brand authority | Unchanged
/pages/ingredients | Our Chocolate | Trust page | Brand Designer | Ingredient transparency | Must launch | Editorial Trust | Links from PDP tabs | Modified | Absorbs /pages/ingredient-transparency (redirect) so there is one ingredient trust page.
/pages/organic-and-fairtrade | Our Chocolate | Trust page | SEO Specialist | Claim proof | Phase 1 if claims exist | Editorial Trust | Avoid greenwashing | Unchanged
/pages/allergens | Our Chocolate | Trust page | Ecommerce Trader | Allergen safety and product trust | Must launch | FAQ/Trust | Also product-level content | Unchanged
/pages/shipping-and-delivery | Delivery | Service page | Ecommerce Trader/Developer | Delivery rules and customer confidence | Must launch | Service | Core conversion page | Unchanged
/pages/delivery-calendar | Delivery | Service page | Shopify Developer | Date picker and shipping calendar logic | Must launch if app ready | Service | Critical for gifts | Unchanged
/pages/warm-weather-shipping | Delivery | Service page | Ecommerce Trader/SEO | Temperature-sensitive shipping clarity | Must launch | Service | Reduces complaints | Unchanged
/pages/returns-and-quality-guarantee | Delivery | Service page | Ecommerce Trader | Quality guarantee and returns policy | Must launch | Service | Risk reduction | Unchanged
/pages/faq | Delivery | FAQ | Ecommerce Trader | Support deflection | Must launch | FAQ | Shipping, gifting, vegan, allergens, corporate | Unchanged
/collections/small-attentions | Gifts | Redirect | Shopify Developer | 301 to /collections/small-gifts | Must launch | n/a | Keep label "Small Attentions" in nav only if desired | Redirect | Duplicate of small-gifts in nav CSV but not in sitemap.
/pages/ingredient-transparency | Vegan & Conscious | Redirect | Shopify Developer | 301 to /pages/ingredients | Must launch | n/a | Link from Vegan & Conscious nav to /pages/ingredients | Redirect | Duplicate of /pages/ingredients; was in nav CSV only.
/blogs/stories/how-to-store-pralines | Our Chocolate | Blog | SEO Specialist | Informational SEO, product care | Phase 1 | Blog article | Targets "how to store pralines" per SEO map | Added | In SEO keyword map but missing from sitemap.
/blogs/stories | Our Chocolate | Blog index | SEO Specialist | Parent for blog posts | Phase 1 | Blog | Shopify blog handle "stories" | Added | Needed as parent of the SEO blog post.
/pages/about | About | Brand page | Brand Designer | About / brand story landing | Must launch | Editorial Trust | Top nav "About" had no page | Added | Top nav item with no sitemap entry.
/pages/sustainability | About | Trust page | Brand Designer/SEO | Sustainable cacao and ethics claims | Phase 1 if claims exist | Editorial Trust | Shown in design footer. Claims need proof | Added | Footer link in all mockups; not in sitemap.
/pages/contact | About | Service page | Ecommerce Trader | Contact and support | Must launch | Service | Shown in design footer | Added | Footer link in all mockups; not in sitemap.
/pages/build-a-ballotin | Shop | Feature page | TBD | Box builder (pick your own pralines) | TBD: decision needed | Custom | Shown as CTA on Home and in footer. Needs box-builder app/dev | Decision | In design but in no brief or CSV. Cut or scope it.
/policies/privacy-policy | Footer | Legal | Ecommerce Trader | Privacy policy | Must launch | Shopify policy | Use Shopify policy pages | Added | Footer link in designs; legally required.
/policies/terms-of-service | Footer | Legal | Ecommerce Trader | Terms and conditions | Must launch | Shopify policy | Use Shopify policy pages | Added | Footer link in designs; legally required.
/policies/refund-policy | Footer | Legal | Ecommerce Trader | Returns policy (summary links to quality guarantee page) | Must launch | Shopify policy | Align with /pages/returns-and-quality-guarantee | Added | Standard Shopify policy; avoid conflicting returns text.

## Navigation
Top nav (brief) | Dropdown item | URL | Owner | Purpose | Build note | Closest label in design | Change | Reason
Shop | All Chocolates | /collections/all | Shopify UX Designer | Full catalogue | Broad filters | Pralines & Ballotins (design) | Unchanged
Shop | Pralines & Truffles | /collections/pralines-and-truffles | Shopify UX Designer | Core category | Dedicated filters | Pralines & Ballotins (design) | Unchanged
Shop | Ballotins | /collections/ballotins | Shopify UX Designer | Heritage format | Weights/box sizes | Pralines & Ballotins (design) | Unchanged
Shop | Gift Boxes | /collections/gift-boxes | Shopify UX Designer | Gift conversion | Occasion chips | Pralines & Ballotins (design) | Unchanged
Shop | Chocolate Tablets | /collections/chocolate-tablets | Shopify UX Designer | Add-on/lower price | Vegan/dark route | Pralines & Ballotins (design) | Unchanged
Shop | Small Gifts | /collections/small-gifts | Shopify UX Designer | Low-friction gift | Under entry price | Pralines & Ballotins (design) | Unchanged
Shop | Premium Gifts | /collections/premium-gifts | Shopify UX Designer | AOV driver | Premium design | Pralines & Ballotins (design) | Unchanged
Shop | Belgian Classics | /collections/belgian-classics | Shopify UX Designer | Heritage route | SEO/education | Pralines & Ballotins (design) | Unchanged
Shop | Seasonal Drops | /collections/seasonal-drops | Shopify UX Designer | Campaign route | Use disruptor accent | Pralines & Ballotins (design) | Unchanged
Gifts | Birthday Gifts | /collections/birthday-gifts | Shopify UX Designer | Occasion shopping | SEO page | Shop Gifts (design) | Unchanged
Gifts | Thank You Gifts | /collections/thank-you-gifts | Shopify UX Designer | Occasion shopping | High usage | Shop Gifts (design) | Unchanged
Gifts | Love & Romance | /collections/love-and-romance | Shopify UX Designer | Occasion shopping | Valentine ready | Shop Gifts (design) | Unchanged
Gifts | Dinner Party Gifts | /collections/dinner-party-gifts | Shopify UX Designer | Host gift | Small gifts | Shop Gifts (design) | Unchanged
Gifts | Small Gifts (label: Small Attentions) | /collections/small-gifts | Shopify UX Designer | Human label for small gifts | Create collection or redirect to small gifts | Shop Gifts (design) | Modified | Pointed at the single small-gifts collection; old URL redirects.
Corporate Gifts | Corporate Gifting | /pages/corporate-gifting | Shopify UX Designer | B2B overview | Top-priority path | Corporate Gifting (design) | Unchanged
Corporate Gifts | Pralines with Logo | /pages/pralines-with-logo | Shopify UX Designer | Logo praline service | Reference Van Parijs | Corporate Gifting (design) | Unchanged
Corporate Gifts | Client Gifts | /pages/client-gifts | Shopify UX Designer | B2B use case | Can phase content | Corporate Gifting (design) | Unchanged
Corporate Gifts | Employee Gifts | /pages/employee-gifts | Shopify UX Designer | B2B use case | Can phase content | Corporate Gifting (design) | Unchanged
Corporate Gifts | Request a Quote | /pages/request-a-quote | Shopify Developer | Lead capture | Visible CTA | Corporate Gifting (design) | Unchanged
Corporate Gifts | Upload Your Logo | /pages/upload-your-logo | Shopify Developer | File upload | Visible CTA | Corporate Gifting (design) | Unchanged
Vegan & Conscious | Vegan Chocolate | /collections/vegan-chocolates | Shopify UX Designer | Values-led shop | Top-level route | Vegan & Conscious (design) | Unchanged
Vegan & Conscious | Organic | /collections/organic-chocolate | SEO Specialist | Claim page if true | Do not overclaim | Vegan & Conscious (design) | Unchanged
Vegan & Conscious | Fairtrade | /collections/fairtrade-chocolate | SEO Specialist | Claim page if true | Do not overclaim | Vegan & Conscious (design) | Unchanged
Vegan & Conscious | No Alcohol | /collections/no-alcohol-chocolates | Ecommerce Trader | Gift trust | Metafield driven | Vegan & Conscious (design) | Unchanged
Vegan & Conscious | Ingredients & Transparency | /pages/ingredients | Brand Designer | Claim proof | Editorial trust | Vegan & Conscious (design) | Modified | Merged with Ingredients page; old URL redirects.
Our Chocolate | Belgian Pralines | /pages/belgian-pralines | Brand Designer | Heritage education | Editorial page | Our Chocolate (design) | Unchanged
Our Chocolate | Ingredients | /pages/ingredients | Brand Designer | Ingredient trust | PDP support | Our Chocolate (design) | Unchanged | Same URL appears under two nav groups: intentional cross-link, not a duplicate page.
Our Chocolate | Allergens | /pages/allergens | Ecommerce Trader | Safety/compliance | FAQ style | Our Chocolate (design) | Unchanged
Delivery | Shipping Information | /pages/shipping-and-delivery | Ecommerce Trader | Shipping clarity | Core conversion | Not in design (strip only) | Unchanged
Delivery | Delivery Calendar | /pages/delivery-calendar | Shopify Developer | Date logic | Needs app/custom | Not in design (strip only) | Unchanged
Delivery | Warm Weather Shipping | /pages/warm-weather-shipping | Ecommerce Trader | Heat policy | Core chocolate trust | Not in design (strip only) | Unchanged
Delivery | FAQ | /pages/faq | Ecommerce Trader | Support deflection | Launch required | Not in design (strip only) | Unchanged
Corporate Gifts | Corporate Gift Boxes | /collections/corporate-gifts | Shopify UX Designer | Business gift products | Must launch in sitemap but was missing from nav | Corporate Gifting (design) | Added | In sitemap, not in nav CSV.
Corporate Gifts | Seasonal / Hospitality Gifts | TBD | Shopify UX Designer | Use cases shown in Corporate mockup | Only if scope approved | Corporate Gifting (design) | Decision | Mockup shows them; no sitemap pages exist.
Vegan & Conscious | Organic & Fairtrade (proof) | /pages/organic-and-fairtrade | SEO Specialist | Claim proof page | Phase 1 if claims exist | Vegan & Conscious (design) | Added | In sitemap, not in nav CSV.
Delivery | Returns & Quality Guarantee | /pages/returns-and-quality-guarantee | Ecommerce Trader | Risk reduction | Must launch | Not in design (footer only) | Added | In sitemap, not in nav CSV.
About | Our Story | /pages/about | Brand Designer | Brand story | Must launch | About Us (design) | Added | "About" top nav had no destination.
About | Sustainability | /pages/sustainability | Brand Designer/SEO | Ethics and cacao sourcing | Phase 1 if claims exist | About Us (design) | Added | Footer link in designs.
About | Contact | /pages/contact | Ecommerce Trader | Support | Must launch | Footer (design) | Added | Footer link in designs.
Shop | Build a Ballotin | /pages/build-a-ballotin | TBD | Box builder | Decision needed | Home intent card (design) | Decision | Only in design; scope unconfirmed.

## Redirects & Canonicals
From | To / Rule | Type | Reason | Owner
/collections/small-attentions | /collections/small-gifts | 301 redirect | One collection, two labels | Shopify Developer
/pages/ingredient-transparency | /pages/ingredients | 301 redirect | Merge duplicate trust pages | Shopify Developer
Any filtered collection URL (?filter.*) | Parent collection URL | Canonical + noindex rule | Per SEO map: do not index filters | SEO Specialist
/collections/organic-chocolate | Create only if organic SKUs exist | Conditional | Avoid greenwashing; no empty claim pages | SEO Specialist
/collections/fairtrade-chocolate | Create only if Fairtrade SKUs exist | Conditional | Avoid greenwashing; no empty claim pages | SEO Specialist
/collections/all | Self-canonical | Canonical | Auto-generated Shopify collection | SEO Specialist

## Build Checklist
# | Template / area | Task | Type | Owner | Dependency | Gate | Status
1 | Global | Choose theme with filter drawer, mega menu, quick-add, cart drawer | Theme | Shopify Developer | Theme demo checked against all 5 designs | Gate 2 | Not started
2 | Global | Create collections list and automated collection rules from metafields/tags | Setup | Shopify Developer | Metafield schema approved | Gate 4 | Not started
3 | Global | Create all 20 product metafield definitions (add palm_oil_free if claimed) | Setup | Shopify Developer | Schema sign-off | Gate 2 | Not started
4 | Global | Mega menu + mobile menu built from reconciled Navigation sheet | Theme | Shopify Developer | Nav decision (Open Decisions #1) | Gate 4 | Not started
5 | Global | Announcement bar (3 USPs) with only verified claims | Theme | Shopify UX Designer | Claims verified | Gate 4 | Not started
6 | Global | Cart drawer: gift message, delivery date, tablet upsell | Theme/App | Shopify Developer | Cart drawer design (missing) | Gate 3 | Not started
7 | Global | Markets setup: country, currency, language selector | Setup | Shopify Developer | Shipping zones defined | Gate 4 | Not started
8 | Global | Footer links to real pages and Shopify policies | Theme | Shopify Developer | Sitemap additions approved | Gate 4 | Not started
9 | Homepage | Hero + trust chips, 4 intent cards, bestsellers carousel | Theme | Shopify UX Designer | Product photography | Gate 3 | Not started
10 | Homepage | Collection banners, corporate band, delivery confidence panel | Theme | Shopify UX Designer | Delivery rules defined | Gate 4 | Not started
11 | Homepage | Replace placeholder rating (12,000+ reviews) with real review feed or remove | App/Content | Ecommerce Trader | Reviews app chosen | Gate 5 | Not started
12 | Homepage | Build a Ballotin card: build or remove | Decision | Founder/Trader | Open Decisions #2 | Gate 1 | Not started
13 | Collection PLP (All / Gifts / Pralines & Truffles / Gift Boxes) | Product card: badges, piece count, price, quick add, wishlist (if kept) | Theme/App | Shopify Developer | Metafields loaded | Gate 4 | Not started
14 | Collection PLP (All / Gifts / Pralines & Truffles / Gift Boxes) | Filter sets per collection per filter matrix, not all 8 groups | Theme/App | Shopify Developer | Confirm per-collection filter support | Gate 2 | Not started
15 | Collection PLP (All / Gifts / Pralines & Truffles / Gift Boxes) | Price filter: buckets (matrix) vs slider (design) | Decision | Shopify UX Designer | Open Decisions #5 | Gate 3 | Not started
16 | Collection PLP (All / Gifts / Pralines & Truffles / Gift Boxes) | Category chips (Ballotins, Gift Boxes, Small Gifts...) | Theme | Shopify UX Designer | Collections created | Gate 4 | Not started
17 | Collection PLP (All / Gifts / Pralines & Truffles / Gift Boxes) | Gifting strip, trust strip, FAQ, related collections blocks | Theme | Shopify UX Designer | Copy approved | Gate 4 | Not started
18 | Vegan & Conscious landing | Vegan hero, 5 claim tiles, vegan product carousel | Theme | Shopify UX Designer | Vegan SKUs loaded | Gate 4 | Not started
19 | Vegan & Conscious landing | Claim badges driven by vegan/organic/fairtrade/palm-oil metafields | Setup | Shopify Developer | Supplier proof on file | Gate 5 | Not started
20 | Vegan & Conscious landing | Remove Organic/Fair Trade/No palm oil tiles unless proven per SKU | Content | Ecommerce Trader/SEO | Claims audit | Gate 5 | Not started
21 | Corporate Gifting landing | Use-case cards, format cards, personalisation row, delivery strip | Theme | Shopify UX Designer | Scope decision (Open Decisions #6) | Gate 3 | Not started
22 | Corporate Gifting landing | Inline quote form (name, email, company, use case, qty, date, notes) | App/Custom | Shopify Developer | Quote routing decided | Gate 4 | Not started
23 | Corporate Gifting landing | Logo upload field: accepted file types, size limit, artwork approval flow | App/Custom | Shopify Developer | Upload app chosen | Gate 4 | Not started
24 | Corporate Gifting landing | Client logos and testimonial: only with written permission | Content | Founder | Permission obtained | Gate 5 | Not started
25 | Pralines with Logo | Design and build page (not yet designed): MOQ, sample pack CTA, quote CTA | Design/Theme | Shopify UX Designer | MOQ and sample pack offer | Gate 3 | Not started
26 | Product detail page | Gallery (4 views), price + badges, piece count + net weight | Theme | Shopify Developer | Metafields loaded | Gate 4 | Not started
27 | Product detail page | Gift message option (PDP and cart) | App | Shopify Developer | Gift message rules | Gate 4 | Not started
28 | Product detail page | Delivery date estimate + warm weather notice from metafields | App/Custom | Shopify Developer | Heat threshold, cut-offs, blackout dates | Gate 4 | Not started
29 | Product detail page | Allergen summary near Add to Cart (not only in tab) | Theme | Shopify UX Designer | Allergen data per SKU | Gate 4 | Not started
30 | Product detail page | 5 tabs from metafields: Inside the Box, Flavour, Ingredients & Allergens, Delivery & Care, Gifting & Corporate | Theme | Shopify Developer | Content per SKU | Gate 5 | Not started
31 | Product detail page | Related products logic: small add-on, premium upgrade, vegan alt, corporate-eligible | App | Shopify Developer | Search & Discovery recs | Gate 4 | Not started
32 | Request a Quote (standalone) | Standalone quote page (not yet designed) reusing inline form | Design/Theme | Shopify UX Designer | Quote routing decided | Gate 3 | Not started
33 | Delivery / Warm Weather | Design and build shipping, delivery calendar, warm weather, returns pages | Design/Theme | Shopify UX Designer | Shipping rules | Gate 3 | Not started
34 | Delivery / Warm Weather | Delivery date picker app evaluated against heat rules | App | Shopify Developer/Trader | Rules defined first | Gate 4 | Not started
35 | Delivery / Warm Weather | Courier/label app (Sendcloud, ShipStation) configured | App | Ecommerce Trader | Courier and fulfilment model | Gate 4 | Not started
36 | Trading data | Final SKU list, variants, pricing bands, margins | Content | Ecommerce Trader | Strategy sign-off | Gate 1 | Not started
37 | Trading data | Per-SKU content: ingredients, allergens, shelf life, storage, claims, lead time | Content | Ecommerce Trader | Supplier data | Gate 5 | Not started
38 | Trading data | Shipping zones, cut-offs, blackout dates, heat threshold, cold pack, damage policy | Content | Ecommerce Trader | Courier choice | Gate 2 | Not started
39 | SEO | Meta titles/descriptions per sitemap page, canonical rules, schema | SEO | SEO Specialist | Sitemap approved | Gate 5 | Not started
40 | SEO | 301 redirects from Redirects sheet, filter canonicals | SEO | SEO Specialist/Developer | Final URLs | Gate 5 | Not started
41 | SEO | Submit sitemap.xml to GSC after launch | SEO | SEO Specialist | Launch | Post-launch | Not started
42 | Analytics | Implement 14 GA4 events (collection, filter, search, gift message, delivery date, quote, logo upload, purchase) | Analytics | Shopify Developer/SEO | Before soft launch | Gate 4 | Not started
43 | QA | Mobile, checkout, filters, forms, delivery, analytics QA | QA | All | Build complete | Launch gate | Not started

## Open Decisions (hidden)
# | Decision needed | Who decides | Needed by | Note | Answer
1 | Navigation: follow brief (Shop, Gifts, Corporate Gifts, Vegan & Conscious, Our Chocolate, Delivery, About) or the design (adds "Pralines & Ballotins", drops Delivery)? | Founder/UX Designer | Gate 2 | Recommend brief structure; add Delivery to design
2 | Build a Ballotin box builder: in launch scope? | Founder/Trader | Gate 1 | No brief, CSV or schema covers it; needs app/dev
3 | Do 12,000+ reviews, "since 1956", and client logos have real backing? | Founder | Gate 5 | Replace with verified or remove
4 | Which claims are provable per SKU: vegan, organic, Fairtrade, no palm oil? | Trader/SEO | Gate 5 | Add palm_oil_free metafield if kept
5 | Price filter: slider (design) or buckets (filter matrix)? | UX Designer/Trader | Gate 3 | Matrix says buckets
6 | Corporate scope: Seasonal/Hospitality use cases, multiple addresses, invoice support, courier integration? | Trader | Gate 1 | Multi-address needs an app
7 | Small gift entry price: under €15 (design) or under €25 (assortment)? | Trader | Gate 1 | Align copy and filter
8 | Delivery promise "1-2 business days": is it deliverable under heat rules? | Trader | Gate 2 | Do not publish until confirmed
9 | Shopify plan: Plus or not (checkout extensions)? | Founder | Gate 2 | Drives gift message/delivery date placement
10 | Quotes feed: email, CRM or Shopify draft orders? | Developer/Trader | Gate 2 | Needed to pick quote app
11 | Delivery page: one page or two (shipping-and-delivery + warm-weather-shipping)? | Trader/SEO | Gate 2 | Sitemap has two; UX brief says one
12 | Wishlist hearts on product cards: keep? (app needed, not in briefs) | UX Designer | Gate 3 | Optional
13 | Brand name and contact details: replace placeholder Maison Atelier Praline, phone, email, © 2024 | Founder | Gate 3 | Placeholder data in mockups